## Sheet1
Bug | Description | Results Expected | Results Actual | Steps To Reproduce | Date | Severity | Reported By | Assigned To | Status
Player Move Boundary Interaction | The player moves left when I am not pressing any keys. This occurs when I press the opposing key and then release the key opposing that key last. | The player does not automatically move left after pressing the opposing key. | The player does automatically move left after pressing the opposing key. | Move to the right-wall. Then spam horizontal move-inputs “a”/”d” once. Then release the A key first before releasing the D key. The bug will also occur for any other wall. | 2025-02-24 | 3 | Daniel | Kung | To be fixed
Enemy Move Speed Inconsistent | When the player turns to face the mouse after it moves to the opposite side of the player, enemy movement speed unintentionally decreases. | When the player turns, enemy move speed does not decrease. | When the player turns, enemy move speed does decrease. | Spam turns by rapidly moving the mouse to either side of the player. Enemy move speed will decrease. | 2025-02-23 | 2 | Daniel | Haonan | To be fixed
Enemy Spawn Not Random | Enemies do not spawn at completely random locations; instead, they are randomly selected from a set of predefined spawn points. | Enemies spawn at completely random locations. | Enemies do not spawn at completely random locations. | Spam spawn enemy “g” | 2025-02-23 | 5 | Daniel | Haonan | To be fixed
Game Over Screen Missing | The game over screen does not appear. This may be because the texture is rendered off-camera. A temporary-fix was implemented by replacing it with a black screen. | The game over screen appears. | The game over screen does not appear. | Die | 2025-03-09 | 3 | Daniel | Anna | To be fixed
Seeds and Towers overlay Toolbar | The seeds and towers are rendered over the toolbar. This has to do with the order in which the seeds and toolbars are rendered. Note that the seeds and towers already render below the player. | The toolbar is rendered over the seeds and towers | The seeds and towers are rendered over the toolbar | Plant a seed on the farmland, and then have the toolbar appear over the farmland. | 2025-03-09 | 2 | Daniel | Kung | To be fixed
Plant Seed Position | When the player plants a seed, it is placed in a nearby tile rather than directly on their current tile. | The seed is placed in the current tile. | The seed is placed in a current tile. | Press “F” to plant seed. | 2025-03-09 | 2 | Daniel | Kung | To be fixed
Sign renders too close to farmland | The sign renders too close to farmland. | There is some distance between the sign and the farmland. | The sign is on the farmland. | Go into tutorial mode. | 2025-03-09 | 4 | Kung | Kung | To be fixed
Player State System | The player does not have a proper state system. As a result, it is possible for the player to be in the move/idle state when performing an attack. | The player has a state system. | The player does not have a state system. | n/a | 2025-03-18 | 4 | Daniel | Daniel | To be fixed
Player Attack Crash | It is difficult to reproduce this bug, but I remember spam-attacking the enemies in the tutorial. | The player performs the attack and deals damage and knockback and particle effect on the enemy | Game crashes | spam attack enemies | 2025-03-18 | 1 | Daniel | Haonan | To be fixed
Scorched Earth Size | The scorched earth does not extend to the boundaries of the map. Originally, the scorched earth was rendered using large tiles that covered the entire screen. To improve FPS, I created a hole in the scorched earth to let the grass background show through. However, because of the large tile size, this caused misalignment with the map boundaries. To fix this, I reduced the tile size of the scorched earth to match the rest of the tileset, which corrected the alignment. However, increasing the number of scorched earth tiles leads to a drop in FPS. I am unsure if I would consider this a bug. | The scorched earth extends to the boundaries of the map. | The scorched earth does not extend to the boundaries of the map. | Renders automatically when game starts | 2025-03-22 | 4 | Daniel | Kung | To be fixed
Save Game - Chicken Summoned | When chicken is summoned on the screen, press = will save the game, and when reload the game the mesh collision does not work anymore. | Should not be able to save the game. It is a design choice as well as you cannot save during a cutscene. | Game can still be saved and cause problems. It’s because we did not save the Mesh*. | Press C to summon chicken Press = when chicken is still on the screen to save the game |  | 1 | Ziqing | Ziqing | To be fixed
Seeds do not match if different seed is initialized | If current_seed is changed, the seed being planted remains the first seed. In addition, this mismatch creates another bug in which the game fails to close with the ESC button. | The seed being planted is the seed that is being instantiated. The game closes. | The seed being planted is the first seed. The game crashes without actually closing. | Plant a seed. Quit the game. | 2025-03-24 | 1 | Kung | Kung | To be fixed