## Bug Report
Bug | Description | Results Expected | Results Actual | Steps To Reproduce | Date | Severity | Reported By | Assigned To | Status
Player Move Boundary Interaction | The player moves left when I am not pressing any keys. This occurs when I press the opposing key and then release the key opposing that key last. | The player does not automatically move left after pressing the opposing key. | The player does automatically move left after pressing the opposing key. | Move to the right-wall. Then spam horizontal move-inputs “a”/”d” once. Then release the A key first before releasing the D key. The bug will also occur for any other wall. | 2025-02-24 | 3 | Daniel | Kung
Enemy Move Speed Inconsistent | When the player turns to face the mouse after it moves to the opposite side of the player, enemy movement speed unintentionally decreases. | When the player turns, enemy move speed does not decrease. | When the player turns, enemy move speed does decrease. | Spam turns by rapidly moving the mouse to either side of the player. Enemy move speed will decrease. | 2025-02-23 | 2 | Daniel | Haonan
Enemy Spawn Not Random | Enemies do not spawn at completely random locations; instead, they are randomly selected from a set of predefined spawn points. | Enemies spawn at completely random locations. | Enemies do not spawn at completely random locations. | Spam spawn enemy “g”. | 2025-02-23 | 5 | Daniel | Haonan
Enemy Texture Glitch | There is a weird texture glitch above some of the zombie sprites. This may be related to how they are rendered or improper scale. | There is no texture glitch. | There is a texture glitch. | Spawn a lot of zombies. | 2025-02-24 | 3 | Daniel | Daniel
Player Attack Animation Fail | When the player attacks, the player sprite animation may fail to occur. Usually, this does not occur, and is only noticeable when spamming attacks very quickly. | When the player attacks, the player sprite animation plays. | When the player attacks, the player sprite animation fails. | Spam Attack. | 2025-03-04 | 4 | Daniel | Daniel
Game Over Screen Missing | The game over screen does not appear. | The game over screen appears. | The game over screen does not appear. | Die. | 2025-03-09 | 3 | Daniel | Anna
Farmland Position | The farmland is not located in the centre of the map. | The farmland is in the centre of the map. | The farmland is not in the centre of the map. | Open the game. | 2025-03-09 | 3 | Daniel | Ziqing
Skeleton Knockback | The skeleton does not get knocked back when attacked by the player. | When the player attacks a skeleton, they are knocked back. | When the player attacks a skeleton, they are not knocked back. | Attack a skeleton with the player. | 2025-03-09 | 3 | Daniel | Haonan
Seeds and Towers Overlay Toolbar | The seeds and towers are rendered over the toolbar. | The toolbar is rendered over the seeds and towers | The seeds and towers are rendered over the toolbar | Plant a seed on the farmland, and then have the toolbar appear over the farmland. | 2025-03-09 | 3 | Kung | Kung
Skeleton Fail Attack B | If the player moves within range of the skeleton while it is attacking a plant, the skeleton will do nothing. | The skeleton continues to attack. | The skeleton does nothing. | Press “0” to spawn a skeleton. | 2025-03-09 | 2 | Daniel | Haonan
Plant Seed Position | When the player plants a seed, it is placed in a nearby tile rather than directly on their current tile. | The seed is placed in the current tile. | The seed is placed in a nearby tile. | Press “f” to plant seed. | 2025-03-09 | 2 | Daniel | Kung
Sign renders too close to farmland | The sign renders too close to farmland. | There is some distance between the sign and the farmland. | The sign is on the farmland. | Go into tutorial mode. | 2025-03-09 | 4 | Kung | Kung
Inventory Offset | The inventory doesn't render smoothly with the camera's position—it feels slightly off. | n/a | n/a | n/a | 2025-03-09 | 4 | Daniel | Kung
Auto-Summon Chicken Fail | The chicken is automatically summoned when the player's health drops below 1/4. However, if the player restarts the game after the effect has been triggered once, it does not occur again. | The effect can be triggered again. | The effect cannot be triggered again. | n/a | 2025-03-09 | 4 | Daniel | Haonan
Skeleton Fail Attack C | If the player moves out of range during the skeleton’s first attack animation, they will remain in the attack pose as they move toward the player. | The skeleton resets to the move animation. | The skeleton remains in the attack pose. | n/a | 2025-03-09 | 3 | Daniel | Haonan
Note on A1: Indicate the bug title and add a URL to a new document. Document - Description - Expected - Actual - Reproduce
Note on G1: 0 = crash bug 1 = game stopping but not crash, 2 = not working as expected 3 = annoying 4 = nice to have 5 = future release
Note on H1: Indicate the person who reported the bug.
Note on I1: Indicate the person who is assigned this bug.
Note on J1: Indicate "T" if the bug is fixed.