## Sheet1
Bug | Description | Results Expected | Results Actual | Steps To Reproduce | Date | Severity | Reported By | Assigned To | Status
Player Move Boundary Interaction | The player moves left when I am not pressing any keys. This occurs when I press the opposing key and then release the key opposing that key last. | The player does not automatically move left after pressing the opposing key. | The player does automatically move left after pressing the opposing key. | Move to the right-wall. Then spam horizontal move-inputs “a”/”d” once. Then release the A key first before releasing the D key. The bug will also occur for any other wall. | 2025-02-24 | 3 | Daniel | Kung | To be fixed
Enemy Move Speed Inconsistent | When the player turns to face the mouse after it moves to the opposite side of the player, enemy movement speed unintentionally decreases. | When the player turns, enemy move speed does not decrease. | When the player turns, enemy move speed does decrease. | Spam turns by rapidly moving the mouse to either side of the player. Enemy move speed will decrease. | 2025-02-23 | 2 | Daniel | Haonan | To be fixed
Player Movement Bug (Cutscene) | The player movement bug from way before has resurfaced due to cutscenes. Note that the partial fix works here as well. | The user can control the player after the cutscene ends. | The user cannot control the player after the cutscene ends unless they reach a boundary. | Trigger a cutscene while the player is moving. | 2025-04-01 | 4 | Kung | All | To be fixed
Load/Restart Crash | The following command-sequence will crash the game. Load Game Restart Load Game Restart (crash) Upon testing, this only occurs if Restart is pressed immediately after Load Game. (or spam it) When you check the json file, hp_percentage is NULL, and it cause NULL assignment to crash the game. | The command-sequence does not crash the game. | The command-sequence does crash the game. | Perform the command-sequence. | 2025-04-03 | 4 | Daniel | Daniel/Haonan | To be fixed
Reloadability Move Bug | If the game is saved while the player is moving, then upon loading, the player continues to move even without any keys being pressed. This is not a bug, as the motion component is correctly saved and loaded. However, the player's velocity should be reset to 0 upon loading. This issue also reveals a second bug: a duplicate pause button appears and moves to the right when the game is loaded. Further testing indicates this only occurs when the game is saved, not loaded. | The player does not move when loading the game. There is no duplicate pause button. | The player does move when loading the game. There is a duplicate pause button. | press either WASD and then save the game | 2025-04-03 | 4 | Daniel | Kung | To be fixed
Music does not play after returning from Game Over | The music does not play once you leave the game over screen with the buttons | The day_BGM plays once you reach the cutscene or the splash screen (main menu) | Day_BGM does not play. | Exit the game over screen using the buttons. | 2025-04-07 | 4 | Kung | Ziqing | To be fixed
HP bar increases | The HP bar increases. This is a very rare bug, but I was able to reproduce it once. It was not the first time it happened. Since it is super rare, it might not be worth it to fix it, but I have it here just in case one encounters it. | The HP bar decreases when enemies attack. | The HP bar increases | Have multiple enemies on the screen. Maybe level up while you do so?? | 2025-04-08 | 4 | Kung | Kung | To be fixed
Reloadability Electricity Crash | Saving the game when there are at least two electricity towers present will result in a crash upon load. This bug does not occur if the second motion component is removed from createElectricityEffect. | game loads | game load crashes | Save game when more than 2 electricity towers, then load game | 2025-04-09 | 4 | Daniel | Daniel | To be fixed
Reloadability Inventory Select | If I load the game from the start screen without starting a new game first, using the number keys to select a new seed causes the game to crash. This only happens after closing and reopening the game. | game loads | game load crashes | Load game from splash screen, press number key to select seeds | 2025-04-10 | 4 | Daniel | Daniel | To be fixed
Scorched Earth Size | The scorched earth does not extend to the boundaries of the map. Originally, the scorched earth was rendered using large tiles that covered the entire screen. To improve FPS, I created a hole in the scorched earth to let the grass background show through. However, because of the large tile size, this caused misalignment with the map boundaries. To fix this, I reduced the tile size of the scorched earth to match the rest of the tileset, which corrected the alignment. However, increasing the number of scorched earth tiles leads to a drop in FPS. I am unsure if I would consider this a bug. | The scorched earth extends to the boundaries of the map. | The scorched earth does not extend to the boundaries of the map. | Renders automatically when game starts | 2025-03-22 | 4 | Daniel | Kung | To be fixed
Skeleton Archer Freeze | There is a skeleton that will freeze at the top of the map. This was common during cross-play. A hypothesis is that this only occurs if a plant is on the border of the map. A suggestion is remove the row/column of farm tiles on the edge of the map. | Skeleton move towards player | Skeleton freeze | Just play the game at the map border | 2025-04-10 | 1 | Daniel | Haonan | To be fixed